**OBSERVATION: Hopes & Dreams future house**

**WHOM: Father & Pelle**

**DATE: 04-09-2017**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Time** | **Activity** | **Duration** | **Family member’s state: from relaxed(0) to anxious(5)** | **Actor’s style of work: from withdrawn(0) to dominant(5)** | **Answer formulation: Family member formulates answer(0) to team member formulates the answer(5)** | **Level of participation (family member): from no participation (0) to full participation (5)** | **Speed of workshop: too slow(0) to too fast(5)** | **Support level fulfilment: none (0), following all the steps(5)** | **Comment** | **Picture** |
| 09:00 | Seating and preparation | 15 min | 1 | 2 | - | - | 1 | 4 | The family member seems relaxed an welcoming |  |
| 09:15 | Step 1: Introduction | 5 min | 3 | 4 | - | - | 2 | 5 | Pelle is using the support to the letter. The participant (father) seems to struggle a little to follow what is requested. |  |
| 09:20 | Step 2: Drawing | 10 min | 5 | 4 | 4 | 5 | 4 | 0 | The workshop is going too fast participant is struggling to keep up. Support should be changed |  |
| 09:30 | Step 3: feedback | 5 min | 4 | 3 | - | 2 | 4 | 0 |  |  |
| 09:35 | Step 4: Drawing | 15 min | 3 | 3 | 3 | 4 | 3 | 4 |  |  |
| 09:50 | Step 5: feedback | 5 min | 2 | 2 | 2 | 2 | 2 | 5 |  |  |
| 09:55 | Step 6: Drawing | 15 min | 2 | 1 | 2 | 4 | 3 | 4 |  |  |
| 10:10 | Step 7: Summing up | 5 min | 1 | 2 | 3 | 2 | 1 | 5 |  |  |

|  |  |
| --- | --- |
| **Number** | **Feedback** |
| 1 | I think Pelle is very good in making the participant feel at ease |
| 2 | Pelle is using the support to read at loud, this is a little impersonal to the participant. |
| 3 | The participant is not getting enough time to draw, the support should be altered |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |

|  |  |
| --- | --- |
| **Number** | **Decisions** |
| 1 | Pelle will try to be more relaxed during the workshop to make the participant feel at ease. |
| 2 | Pelle will try to rehearse the support a more before the workshop will start. In this way he can explain more naturally what they are going to do. |
| 3 | A review has been written in our books to Michiel and also written down in the digital feedback document, so more time can be given. |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |